## Summary
Field | Value | Details
Project | NVIDIA AIQ Skills and OpenClaw Enablement | AIQ parity package modeled after the RAG/VSS skills process.
Generated On | 2026-05-12 | Use this workbook with skills/TRACKER.md for execution tracking.
Current Stage | Preview implementation complete; runtime validation pending | Docs, skills, evals, CI gate, OpenClaw scaffold, Word playbook, and Excel tracker are present.
Done Items | 14 | Inventory, catalog, skills, evals, playbook, OpenClaw scaffold, compliance checker, CI, PR template, docx, and xlsx.
In Progress Items | 1 | Reference deepening and real-world validation examples.
Todo Items | 7 | Security review, runtime validation, OpenClaw install validation, CODEOWNERS, and catalog publication.
Focused Skills | 10 | All use aiq-* names and include SKILL.md, references, and evals.
Behavioral Eval Cases | 30 | At least 3 per skill, including negative or security scenarios.
Existing Skill | .agents/skills/aiq-research retained | Mapped to aiq-run-research and aiq-manage-jobs instead of replacing the stable helper.
Primary Tracker | skills/TRACKER.md | Markdown execution tracker in source control.
Excel Tracker | project-artifacts/trackers/AIQ_Skills_Project_Tracker.xlsx | Workbook version for program tracking and stakeholder review.
Word Playbook | project-artifacts/skills/AIQ_Skills_Playbook.docx | Generated from skills/PLAYBOOK.md.

## Work Items
ID | Phase | Work Item | Owner | Priority | Status | Start | Target | Actual/Next | Dependency | Artifact | Notes
AIQ-001 | Inventory | Inventory existing aiq-research skill | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | AIQ checkout | .agents/skills/aiq-research | Stable helper retained and mapped to focused catalog owners.
AIQ-002 | Inventory | Inventory AIQ docs, configs, deploy, frontends, sources, and tokenomics | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | AIQ checkout | README.md; docs/source; configs; deploy; frontends; sources | Source-of-truth paths captured in playbook and references.
AIQ-003 | Inventory | Compare AIQ needs with RAG/VSS skill process | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | RAG/VSS sample | skills/PLAYBOOK.md | Same catalog/playbook/tracker/evals/compliance/OpenClaw pattern applied.
AIQ-004 | Catalog | Create AIQ skills catalog README | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Inventory | skills/README.md | Catalog, install guidance, and existing skill ownership map added.
AIQ-005 | Catalog | Scaffold ten focused aiq-* skills | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Catalog design | skills/aiq-* | Setup, deploy, research, jobs, agents, tools, knowledge, eval, tokenomics, troubleshoot.
AIQ-006 | Catalog | Add skill references for source maps and workflow details | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | AIQ docs | skills/aiq-*/references/*.md | Each skill has at least one reference file.
AIQ-007 | Evals | Add behavioral evals with negative/security coverage | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Skill scaffold | skills/aiq-*/evals/evals.json | Compliance checker validates case shape and safety gates.
AIQ-008 | Playbook | Create comprehensive AIQ skills playbook | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | RAG/VSS sample | skills/PLAYBOOK.md | Defines naming, metadata, security, review, lifecycle, OpenClaw, and eval standards.
AIQ-009 | Tracker | Create Markdown execution tracker | Skills owner | Medium | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Playbook | skills/TRACKER.md | Tracks phases and publication readiness.
AIQ-010 | OpenClaw | Create OpenClaw manifest, workspace docs, and skill symlinks | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Skill catalog | .openclaw/ | Manifest and workspace docs added. Runtime install remains pending.
AIQ-011 | Governance | Add compliance checker and CI gate | Skills owner | High | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Skill schema | scripts/skill_compliance_check.py; .github/workflows/ci.yml | Checker passes locally for current catalog.
AIQ-012 | Governance | Add PR checklist for skills and OpenClaw changes | Skills owner | Medium | Done | 2026-05-11 | 2026-05-11 | 2026-05-11 | Governance | .github/PULL_REQUEST_TEMPLATE.md | Checklist covers evals, destructive confirmation, runtime data handling, and signoff.
AIQ-013 | Artifacts | Generate Word playbook | Skills owner | Medium | Done | 2026-05-12 | 2026-05-12 | 2026-05-12 | skills/PLAYBOOK.md | project-artifacts/skills/AIQ_Skills_Playbook.docx | Generated with Pandoc from source Markdown.
AIQ-014 | Artifacts | Generate Excel project tracker | Skills owner | Medium | Done | 2026-05-12 | 2026-05-12 | 2026-05-12 | Tracker model | project-artifacts/trackers/AIQ_Skills_Project_Tracker.xlsx | Workbook includes summary, work items, skill catalog, risks, timeline, and review findings.
AIQ-015 | Hardening | Deepen references with mode-specific commands and failure paths | AIQ engineering | Medium | In Progress | 2026-05-12 | 2026-05-13 | Add examples from local server, Docker, Helm, NAT, eval, and tokenomics runs | Runtime validation | skills/aiq-*/references/*.md | Current references are complete enough for preview; production examples need real run evidence.
AIQ-016 | Validation | Run local API/server/UI research workflows with skills | AIQ engineering | High | Todo |  | 2026-05-18 | Capture commands, logs, and fixes | Working dev environment and keys | docs/source/integration; frontends | Do not publish until real local-server workflows are exercised.
AIQ-017 | Validation | Run Docker Compose and Helm validation paths | Deployment owner | High | Todo |  | 2026-05-18 | Capture deployment matrix | Container and cluster access | deploy/compose; deploy/helm | Confirm teardown gates and data retention wording.
AIQ-018 | Security | Complete security review for keys, external tools, JWT/auth, eval data, and destructive actions | Security reviewer | High | Todo |  | 2026-05-15 | Record signoff and required changes | Skill package | SECURITY.md; .github/PULL_REQUEST_TEMPLATE.md | Required before broader distribution.
AIQ-019 | OpenClaw | Validate OpenClaw plugin install and runtime loading | Skills platform reviewer | High | Todo |  | 2026-05-20 | Run install and smoke test | OpenClaw runtime | .openclaw/openclaw.plugin.json | Manifest is scaffolded; runtime install was not run.
AIQ-020 | Governance | Assign CODEOWNERS or reviewer teams for skills and OpenClaw | AIQ maintainers | Medium | Todo |  | 2026-05-15 | Add owner mapping | Team ownership decision | CODEOWNERS | Current PR template has placeholders but not enforcement.
AIQ-021 | Publication | Approve central skills catalog sync | Skills publication owner | Medium | Todo |  | 2026-05-22 | Catalog publication request approved | Security and runtime validation | skills/README.md; .openclaw/ | Publication path still needs platform-owner approval.
AIQ-022 | Evidence | Attach sample validated traces, reports, and benchmark outputs | AIQ engineering | Medium | Todo |  | 2026-05-20 | Store sanitized evidence or links | Runtime validation | project-artifacts/evidence/ | Use sanitized artifacts only; no secrets, raw prompts, or confidential data.

## Skills Catalog
Skill | Path | Primary Outcome | Owner | Status | Eval Cases | OpenClaw Path | Primary Sources | Security/Data Gates | Next Validation
aiq-setup-environment | skills/aiq-setup-environment | Install dependencies and validate Python, uv, Node, API keys, env files, and local prerequisites. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-setup-environment | README.md; docs/source/get-started | Never print secrets; verify env vars by name only. | Run on clean workstation.
aiq-deploy-blueprint | skills/aiq-deploy-blueprint | Start, verify, stop, or tear down scripts, Docker Compose, Helm, web, API, and NAT deployment modes. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-deploy-blueprint | deploy/; docs/source/deployment; scripts/ | Confirm destructive teardown and persisted data deletion. | Smoke test scripts, Compose, Helm.
aiq-run-research | skills/aiq-run-research | Run shallow or deep research through CLI, NAT, local API, web UI, or existing packaged aiq-research helper. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-run-research | configs/; frontends/; .agents/skills/aiq-research | Classify confidential prompts before external providers; preserve citations. | Run CLI, API, web, helper paths.
aiq-manage-jobs | skills/aiq-manage-jobs | Manage async jobs, status, state, reports, SSE events, cancellation, and event-store troubleshooting. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-manage-jobs | frontends/aiq_api; docs/source/integration/rest-api.md | Validate job IDs; confirm cancel/delete actions. | Exercise job lifecycle on local server.
aiq-configure-agents | skills/aiq-configure-agents | Configure agents, LLM roles, prompts, HITL, routing, frontier model settings, and workflow YAML. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-configure-agents | configs/; src/aiq_agent/agents; docs/source/customization | Do not reveal API keys; confirm persistent prompt/config changes. | Run config swap and prompt validation.
aiq-configure-tools | skills/aiq-configure-tools | Configure Tavily, Serper, Exa, Google Scholar, MCP tools, registry entries, and custom tools. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-configure-tools | sources/; docs/source/customization/tools-and-sources.md | Check keys without printing; confirm confidential queries before external calls. | Validate each configured provider path.
aiq-manage-knowledge | skills/aiq-manage-knowledge | Operate LlamaIndex, Chroma, Foundational RAG, ingestion, retrieval, summaries, and TTL/data retention. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-manage-knowledge | sources/knowledge_layer; src/aiq_agent/knowledge; tests/knowledge_layer_tests | Classify docs before ingestion; confirm data deletion. | Run LlamaIndex and foundational RAG scripts.
aiq-evaluate-benchmarks | skills/aiq-evaluate-benchmarks | Run FreshQA, DeepResearch Bench, DeepSearch QA, NAT eval, dataset preparation, and benchmark export workflows. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-evaluate-benchmarks | frontends/benchmarks; docs/source/evaluation | Classify datasets; confirm overwrite of benchmark results. | Run one small benchmark scenario.
aiq-analyze-tokenomics | skills/aiq-analyze-tokenomics | Generate tokenomics, cost, latency, and comparison reports from NAT profiler traces. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-analyze-tokenomics | src/aiq_agent/tokenomics; docs/source/profiling | Sanitize traces; confirm publishing or overwriting reports. | Generate single and comparison reports.
aiq-troubleshoot-blueprint | skills/aiq-troubleshoot-blueprint | Diagnose setup, deployment, API, UI, NAT, tools, jobs, knowledge, eval, and tokenomics failures. | nvidia-aiq-team | Done | 3 | .openclaw/skills/aiq-troubleshoot-blueprint | docs/source/resources/troubleshooting.md; tests/; deploy/ | Read-only diagnostics first; sanitize logs; confirm cleanup actions. | Run failure-mode drills.
aiq-research existing helper | .agents/skills/aiq-research | Stable packaged local-server helper for routed chat and async job lifecycle. | existing package owner | Retained |  | .claude/skills/aiq-research symlink | .agents/skills/aiq-research | No replacement; route overlapping work through focused skills when broader context is needed. | Keep compatibility tests with local server helper.

## Risk Register
ID | Risk | Impact | Likelihood | Mitigation | Owner | Status | Due
R-001 | Skills drift from AIQ docs or runtime behavior. | High | Medium | Use source-of-truth links, compliance checks, and runtime validation before publication. | AIQ engineering | Open | 2026-05-18
R-002 | Secrets leak through examples, logs, traces, or env checks. | High | Medium | Checker scans common secret patterns; skills instruct agents to verify key names without printing values. | Security reviewer | Open | 2026-05-15
R-003 | External search providers receive confidential prompts or documents. | High | Medium | Skills require data classification and explicit confirmation before external calls. | Security reviewer | Open | 2026-05-15
R-004 | Destructive cleanup, job cancellation, or persisted-store deletion occurs without approval. | High | Low | Skills and evals require explicit confirmation gates for destructive operations. | AIQ engineering | Open | 2026-05-15
R-005 | OpenClaw manifest shape changes or runtime install differs from scaffold. | Medium | Medium | Validate against actual OpenClaw runtime before publication. | Skills platform reviewer | Open | 2026-05-20
R-006 | Existing aiq-research helper and new catalog create trigger overlap. | Medium | Medium | README maps ownership; broad workflows route to aiq-run-research and aiq-manage-jobs while existing helper remains stable. | Skills owner | Mitigated | 2026-05-11
R-007 | Benchmark or tokenomics artifacts include sensitive user data. | High | Medium | Classify datasets and traces, sanitize evidence, and require confirmation before publishing reports. | Security reviewer | Open | 2026-05-20
R-008 | CI catches shape issues but not behavioral quality. | Medium | High | Add runtime smoke tests and agent-driven eval review before catalog publication. | Skills owner | Open | 2026-05-18

## Timeline
Milestone | Start | Target | Actual | Status | Exit Criteria | Notes
Inventory and comparison | 2026-05-11 | 2026-05-11 | 2026-05-11 | Done | Existing helper and AIQ docs mapped to focused skill owners. | Completed.
Preview skill catalog | 2026-05-11 | 2026-05-11 | 2026-05-11 | Done | Ten focused aiq-* skills with references and evals exist. | Completed.
Playbook, tracker, and OpenClaw scaffold | 2026-05-11 | 2026-05-11 | 2026-05-11 | Done | Markdown playbook/tracker and OpenClaw manifest/workspace committed. | Runtime install still pending.
Compliance and PR gates | 2026-05-11 | 2026-05-11 | 2026-05-11 | Done | Checker passes locally and CI job exists. | CODEOWNERS still pending.
Stakeholder artifacts | 2026-05-12 | 2026-05-12 | 2026-05-12 | Done | Word playbook and Excel project tracker generated. | This workbook is the tracker artifact.
Reference deepening | 2026-05-12 | 2026-05-13 |  | In Progress | References include run evidence and mode-specific failure paths. | Needs real commands/logs from validation.
Security review |  | 2026-05-15 |  | Todo | Security reviewer signs off on secret, data, external-provider, auth, and destructive-action gates. | Required before publication.
Runtime validation |  | 2026-05-18 |  | Todo | Local server, CLI/NAT, Docker Compose, Helm, benchmarks, knowledge, and tokenomics smoke-tested. | Use sanitized evidence.
OpenClaw runtime validation |  | 2026-05-20 |  | Todo | Plugin installs and routes skills correctly in OpenClaw. | Manifest scaffold only so far.
Publication readiness |  | 2026-05-22 |  | Todo | Reviewer owners assigned and central catalog publication approved. | Depends on security and runtime signoff.

## Review Findings
ID | Recommendation / Finding | Decision | Status | Evidence | Owner | Next Step
F-001 | Do not replace the existing packaged aiq-research helper. | Retain helper and map ownership to focused run/jobs skills. | Implemented | skills/README.md; README.md; docs/source/integration/agent-skills.md | Skills owner | Keep compatibility during runtime validation.
F-002 | Use focused skills instead of one broad AIQ skill. | Create ten aiq-* skills by operational domain. | Implemented | skills/aiq-* | Skills owner | Deepen references with runtime evidence.
F-003 | Add evals that test unsafe or negative behavior, not only happy paths. | Each skill has at least three eval cases and a negative/security scenario. | Implemented | skills/aiq-*/evals/evals.json | Skills owner | Run behavioral eval harness when available.
F-004 | Add machine-checkable quality gates. | Add compliance checker and CI job. | Implemented | scripts/skill_compliance_check.py; .github/workflows/ci.yml | Skills owner | Extend checker if platform metadata requirements change.
F-005 | Make OpenClaw packaging explicit. | Add manifest, workspace docs, and skill symlinks. | Implemented | .openclaw/ | Skills platform reviewer | Validate actual OpenClaw install.
F-006 | Create comprehensive playbook comparable to VSS/RAG sample. | Write Markdown source and generate Word artifact. | Implemented | skills/PLAYBOOK.md; project-artifacts/skills/AIQ_Skills_Playbook.docx | Skills owner | Collect reviewer comments in this tracker.
F-007 | Create a project tracker with done, todo, timeline, risks, and ownership. | Generate Excel workbook with six tracking sheets. | Implemented | project-artifacts/trackers/AIQ_Skills_Project_Tracker.xlsx | Skills owner | Use workbook to run remaining validation.
F-008 | Require explicit confirmation before destructive workflows. | Add wording to deploy/jobs/knowledge/eval/tokenomics/troubleshoot skills and eval gates. | Implemented | skills/aiq-*/SKILL.md; evals | AIQ engineering | Verify with live runbooks.
F-009 | Protect API keys, JWT/auth data, prompts, documents, datasets, traces, and reports. | Add data-classification and no-secret handling across skills. | Implemented | skills/PLAYBOOK.md; skill evals; PR checklist | Security reviewer | Complete formal security review.
F-010 | Clarify publication path and reviewer ownership. | Track as remaining governance work. | Todo | skills/TRACKER.md; this workbook | AIQ maintainers | Assign CODEOWNERS or equivalent reviewers.